## Sheet1
Chorley Bunce
Mobile Side Work
Sl. No | Work | Time in Days (Approx.)
1 | Chef Sign up part | 1
2 | Push Notification | 1
3 | Adding Allocation Page | 1
4 | Option for Date and time of delivery, Quick Add feature | 1
5 | Duplicate Order' from Past Order and 'Order Now' in Ongoing Page. It needs to be changed now. Previously when we are placing an order the 'Job Name' was a manual entry field. Now we have to make it a option field and chef has to select one allocation out of many. | 2.5
6 | Also some other web services needs a bit changes like placing order, login, logout(new) etc.
7 | Certificates, Provisioning Profile work with iTunes set up | 1
8 | Testing | 1.5
9 Days approx.
Web/Backend Work
Sl. No | Work | Time in Days (Approx.)
1 | Chefs Dashboard in Changes Adding by SuperAdmin of the chefs related functionalities removed . A new option added for the Accept/Decline .The related web-service for adding Chef registration through the app and its login . | 2 days
2 | In the Allocations (Manage Allocation) the allocation is assigned to the corrousponding chefs accordingly and its validation. A new web-service integrated for the allocation accordingly for the assigned chefs belongs to place order regarding. | 3 days
3 | Changes in the PlaceOrder,Past Order,Duplicate Order and Ongoing Order web-service and its related tables in DataBase for the Alocation . | 2 days
4 | Integrated Push Notification for the chefs and the new Web-service addeded for the notifications. Changes in the databse tables for notification. Webservice changes as of notification tokens. | 3 days
5 | Integrated the list of Orders accordingly in the corresponding View Allocation Name and Changes in the Order Template of same . | 2 days
6 | Testing of all the web services and all functionality | 2 days
14 Days Avg.